## WBS
Work Package and Number
| % Done |  | 55%
| Hours | 40 | 23
| Cost | 300 | 250
| ESD |  | 2017-05-01
| ECD |  | 2017-08-31 | [32 empty] | PJL Major Projects - Ongoing
1 Operation and Organization | [6 empty] | 2 IT Computer and Network Upgrades |  |  |  | 3 Phys 211 Labs - Coordinator M.I-K. |  |  |  | 4 Phys 223 Labs - Coordinator M.I-K. |  |  |  | 5 Phys 227 Labs - Instructor D.F. |  |  |  | 6 Phys 255 Labs - Instructor C.S. |  |  |  | 7 Phys 259 Labs - Coordinator M.I-K. |  |  |  | 8 Phys 323 Labs - Instructor P.L. |  |  |  | 9 Phys 325 Labs - Instructor M.W. |  |  |  | 10 Phys 341 Labs - Instructor D.H. |  |  |  | 11 Phys 365 Labs - Coordinator M.I-K. |  |  |  | 12 Phys 369 Labs - Coordinator M.I-K. |  |  |  | 13 Phys 375 Labs - Instructor W.T. |  |  |  | 14 Phys 397 Labs - Instructor A.H. |  |  |  | 15 Phys 497 Labs - Instructor M.W. |  |  |  | 16 Phys 597 Labs - Instructor A.L.
| 1.1 PJL lab repository and equipment database |  |  | 1.1.1 PJL website |  |  |  | 2.1 Template |  |  |  | 3.1 New 211 Labs Tested |  |  |  | 4.1 Template |  |  |  | 5.1 Template |  |  |  | 6.1 Electric Field Mapping |  |  |  | 7.1 Play-doe Lab |  |  |  | 8.1 Template |  |  |  | 9.1 Electron Diffraction Updated |  |  |  | 10.1 Companion Guides |  |  |  | 11.1 Template |  |  |  | 12.1 Template |  |  |  | 13.1 Michelson Interferometer |  |  |  | 14.1 Minor Corrections |  |  |  | 15.1 Electronics Labs Improved |  |  |  | 16.1 Laser Safety for Quantum Lab
|  |  |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0% |  | % Done |  | 0%
|  |  |  | Hours | 116 | 0 |  | Hours | 0 | 0 |  | Hours | 40 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 43 | 0 |  | Hours | 26 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0 |  | Hours | 0 | 0
|  |  |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 66.6667 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0 |  | Cost | 0 | 0
|  |  |  | ESD |  | 2017-10-23 |  | ESD |  | 0 |  | ESD |  | 2017-10-01 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  | 2017-10-01 |  | ESD |  | 2017-10-01 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  | 0 |  | ESD |  |  |  | ESD |  |  |  | ESD
|  |  |  | ECD |  | 2017-12-22 |  | ECD |  | 0 |  | ECD |  | 2017-10-13 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 2017-10-27 |  | ECD |  | 2017-10-13 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0 |  | ECD |  | 0
|  |  |  | 1.1.2 Repository database |  |  |  | 2.2 Template | [15 empty] | 6.2 Faraday's Law | [11 empty] | 9.2 Compton Scattering Updated |  |  |  | 10.2 Drag Lab Revision | [11 empty] | 13.2 Minor Corrections
|  |  |  | % Done |  | 0% |  | % Done |  | 0% | [13 empty] | % Done |  | 0% | [9 empty] | % Done |  | 0% |  | % Done |  | 0% | [9 empty] | % Done |  | 0%
|  |  |  | Hours | 262 | 0 |  | Hours | 0 | 0 | [13 empty] | Hours | 48 | 0 | [9 empty] | Hours | 0 | 0 |  | Hours | 0 | 0 | [9 empty] | Hours | 0 | 0
|  |  |  | Cost | 0 | 0 |  | Cost | 0 | 0 | [13 empty] | Cost | 208.3333 | 0 | [9 empty] | Cost | 0 | 0 |  | Cost | 0 | 0 | [9 empty] | Cost | 0 | 0
|  |  |  | ESD |  | 2017-10-23 |  | ESD |  | 0 | [13 empty] | ESD |  | 2017-10-01 | [9 empty] | ESD |  | 0 |  | ESD |  | 0 | [9 empty] | ESD |  | 0
|  |  |  | ECD |  | 2018-04-30 |  | ECD |  | 0 | [13 empty] | ECD |  | 2017-11-03 | [9 empty] | ECD |  | 0 |  | ECD |  | 0 | [9 empty] | ECD |  | 0
|  |  |  | 1.1.3 Equipment database | [19 empty] | 6.3 e/m Experiment | [11 empty] | 9.3 Nuclear Decay Updated | [15 empty] | 13.3 Photodetectors for Coherence Length of Light Lab
|  |  |  | % Done |  | 0% | [17 empty] | % Done |  | 0% | [9 empty] | % Done |  | 0% | [13 empty] | % Done |  | 0%
|  |  |  | Hours | 251 | 0 | [17 empty] | Hours | 0 | 0 | [9 empty] | Hours | 0 | 0 | [13 empty] | Hours | 0 | 0
|  |  |  | Cost | 0 | 0 | [17 empty] | Cost | 0 | 0 | [9 empty] | Cost | 0 | 0 | [13 empty] | Cost | 0 | 0
|  |  |  | ESD |  | 2017-10-23 | [17 empty] | ESD |  | 0 | [9 empty] | ESD |  | 0 | [13 empty] | ESD |  | 0
|  |  |  | ECD |  | 2018-04-30 | [17 empty] | ECD |  | 0 | [9 empty] | ECD |  | 0 | [13 empty] | ECD |  | 0
|  |  |  | 1.1.4 Tools for updating and maintaining database | [19 empty] | 6.4 Minor Corrections | [11 empty] | 9.4 Photoelectric Effect Updated | [15 empty] | 13.4 Companion Guides
|  |  |  | % Done |  | 0% | [17 empty] | % Done |  | 0% | [9 empty] | % Done |  | 0% | [13 empty] | % Done |  | 0%
|  |  |  | Hours | 84 | 0 | [17 empty] | Hours | 0 | 0 | [9 empty] | Hours | 0 | 0 | [13 empty] | Hours | 0 | 0
|  |  |  | Cost | 0 | 0 | [17 empty] | Cost | 0 | 0 | [9 empty] | Cost | 0 | 0 | [13 empty] | Cost | 0 | 0
|  |  |  | ESD |  | 2017-10-23 | [17 empty] | ESD |  | 0 | [9 empty] | ESD |  | 0 | [13 empty] | ESD |  | 0
|  |  |  | ECD |  | 2017-12-22 | [17 empty] | ECD |  | 0 | [9 empty] | ECD |  | 0 | [13 empty] | ECD |  | 0
| 1.2 Reorganize Repair Shop | [34 empty] | 9.5 Minor Corrections
| % Done |  | 0% | [32 empty] | % Done |  | 0%
| Hours | 38 | 0 | [32 empty] | Hours | 0 | 0
| Cost | 0 | 0 | [32 empty] | Cost | 0 | 0
| ESD |  | 2017-10-01 | [32 empty] | ESD |  | 0
| ECD |  | 2017-10-27 | [32 empty] | ECD |  | 0
9.6 Rutherford Scattering Expansion
[36 empty] | % Done |  | 0%
[36 empty] | Hours | 0 | 0
[36 empty] | Cost | 0 | 0
[36 empty] | ESD |  | 0
[36 empty] | ECD |  | 0
9.7 Mass Spectrometer Experiment
[36 empty] | % Done |  | 0%
[36 empty] | Hours | 0 | 0
[36 empty] | Cost | 0 | 0
[36 empty] | ESD |  | 0
[36 empty] | ECD |  | 0
Note on C1: Notes regarding the progress of a work package. This includes deliverables completed, holdups (ie parts on order), important notes from meetings, and anything else of interest.
Note on E4: % of work package completed
Note on D5: Number of hours estimated for the work package
Note on E5: Number of hours used to date
Note on D6: Estimated cost of work package
Note on E6: Cost to date of the work package
Note on E7: Estimated Start Date for work package
Note on E8: Estimated Completion Date of work package

## Scope
Scope Statement and Resource Estimate - PJL Major Projects Fall 2017
|  | Work Package |  |  |  | ESD | ECD | Priority
|  | Under Development | [5 empty] | 0
|  | High Priority | [5 empty] | 1
|  | Medium Priority | [5 empty] | 2
|  | Low Priority | [5 empty] | 3
|  | Completed | [5 empty] | 4
1 |  | 1 Operation and Organization
1.1 PJL lab repository and equipment database
| 1.1 |  | 1.1.1 PJL website |  |  | 2017-10-23 | 2017-12-22 | 1
|  |  |  | - | PDFs, Tex, Data, Images, Additional Documents, and/or All can be zipped and downloaded
|  |  |  | - | Security clearance needed to access any documents or source code.
|  |  |  | - | Landing page
|  |  |  | - | Sort function, including by LabID, include no year in most resents, and sort then filter
|  |  |  | - | Safety documents posted
|  |  |  | - | Experiment and room schedule posted
|  |  |  | - | Equipment information displayed, including location, status, alternatives, and manual
|  |  |  | - | Place to post important information or supplemental documents for students
|  |  |  | - | Ability to report issues
|  |  |  | - | Security audit completed
|  |  |  | - | Mobile version working similar to full version
|  |  |  | - | Templates displayed and downloadable
|  |  |  | - | Sample diagrams displayed and downloadable, including source code
|  |  |  | - | Hosted in final location
|  |  |  | - | Process in place for making additions to website functionality in the future
|  |  |  | - | New pjl logo
|  |  |  | - | Document outlining operational requirements for website
|  |  | 1.1.2 Repository database |  |  | 2017-10-23 | 2018-04-30 | 1
|  |  |  | - | Every lab has a list of equipment that matches the equipment database
|  |  |  | - | Disciplines, topics, and type information added to each lab
|  |  |  | - | Add support documents to repository
|  |  | 1.1.3 Equipment database |  |  | 2017-10-23 | 2018-04-30 | 2
|  |  |  | - | Standardized list of names synced with repository database
|  |  |  | - | Location of all standard equipment, including alternate location
|  |  |  | - | Status of all standard equipment
|  |  |  | - | Manual for standard equipment
|  |  |  | - | Non-standard equipment moved to storage
|  |  |  | - | Standard equipment re-organized in lab rooms
|  |  | 1.1.4 Tools for updating and maintaining database |  |  | 2017-10-23 | 2017-12-22 | 2
|  |  |  | - | Tool to update status of equipment displayed on repository website
|  |  |  | - | Tool to add new lab
|  |  |  | - | Tool to add new versions of labs
|  |  |  | - | Manuals for tools
|  |  |  | - | Document compiled for entire website
|  |  | 1.2 Reorganize Repair Shop |  |  | 2017-10-01 | 2017-10-27 | 1
|  |  |  | - | Parts organized
|  |  |  | - | Electrical upgraded
|  |  |  | - | Manuals moved into repair room
2 IT Computer and Network Upgrades
|  |  | 2.1 Template |  |  |  |  | 0
|  |  | 2.2 Template |  |  |  |  | 0
3 Phys 211 Labs - Coordinator M.I-K.
|  |  | 3.1 New 211 Labs Tested |  |  | 2017-10-01 | 2017-10-13 | 1
|  |  |  | - | Labs tested to endure they are technically sound.
|  |  |  | - | Document outlining any technical issues encountered
|  |  |  | - | Solutions found to any technical issues
|  |  |  | - | Submitted to course coordinator
|  |  |  | - | Sample data collected and compiled
4 Phys 223 Labs - Coordinator M.I-K.
|  |  | 4.1 Template |  |  |  |  | 0
5 Phys 227 Labs - Instructor D.F.
|  |  | 5.1 Template |  |  |  |  | 0
6 Phys 255 Labs - Instructor C.S.
|  |  | 6.1 Electric Field Mapping |  |  | 2017-10-01 | 2017-10-27 | 1
|  |  |  | - | Experimental procedure for producing equipotential lines that are roughly evenly spaced.
|  |  |  | - | Equipment modification made as required to accommodate experimental procedure.
|  |  |  | - | Changes approved by instructor, AHU.
|  |  |  | - | Equipment tested to ensure that it is working correctly
|  |  | 6.2 Faraday's Law |  |  | 2017-10-01 | 2017-11-03 | 1
|  |  |  | - | Equipment reevaluated and updated
|  |  |  | - | More extensive theory
|  |  |  | - | More precise experimental procedure
|  |  |  | - | Changes approved by instructor, technicians, TLDC, and AHU
|  |  | 6.3 e/m Experiment |  |  |  |  | 2
|  |  |  | - | Changes to document approved by instructor and AHU
|  |  | 6.4 Minor Corrections |  |  |  |  | 3
|  |  |  | - | Minor corrections made to the remainder of the labs in response to feedback
|  |  |  | - | Changes approved by instructor and AHU
7 Phys 259 Labs - Coordinator M.I-K.
|  |  | 7.1 Play-doe Lab |  |  | 2017-10-01 | 2017-10-13 | 1
|  |  |  | - | Proposed method to keep play-doe hydrated during the year
|  |  |  | - | New method tested
|  |  |  | - | Document outlining method
|  |  |  | - | Procured play-doe for Winter 2018
8 Phys 323 Labs - Instructor P.L.
|  |  | 8.1 Template |  |  |  |  | 0
9 Phys 325 Labs - Instructor M.W.
|  |  | 9.1 Electron Diffraction Updated |  |  |  |  | 3
|  |  |  | - | Cameras used for data collection
|  |  |  | - | Data obtained from image analysis
Lab write-up modified to accommodate new data collection method
|  |  |  | - | Companion guide updated
|  |  |  | - | Changes to lab write-up approved by instructor and AHU
|  |  | 9.2 Compton Scattering Updated |  |  |  |  | 2
|  |  |  | - | Companion guide updated
|  |  |  | - | Changes to lab write-up approved by instructor and AHU
|  |  | 9.3 Nuclear Decay Updated |  |  |  |  | 2
|  |  |  | - | New sample data using new equipment
|  |  |  | - | Companion guide updated
|  |  | 9.4 Photoelectric Effect Updated |  |  |  |  | 2
|  |  |  | - | New current meter tested
|  |  |  | - | Current meter added if it is an improvement
|  |  |  | - | Companion guide updated
|  |  |  | - | Changes to lab write-up approved by instructor and AHU
|  |  | 9.5 Minor Corrections |  |  |  |  | 3
|  |  |  | - | Minor corrections made to the remainder of the labs in response to feedback
|  |  |  | - | Approved by instructor, technicians, TLDC, and AHU
|  |  | 9.6 Rutherford Scattering Expansion |  |  |  |  | 3
|  |  |  | - | New detector procured
|  |  |  | - | Second vacuum system procured
|  |  |  | - | New target procured
|  |  |  | - | Write-up reworked around new equipment
|  |  |  | - | Space procured to accommodate two setups
|  |  |  | - | Companion guide updated
|  |  |  | - | Approved by instructor, technicians, TLDC, and AHU
|  |  | 9.7 Mass Spectrometer Experiment |  |  |  |  | 0
10 Phys 341 Labs - Instructor D.H.
|  |  | 10.1 Companion Guides |  |  |  |  | 0
|  |  | 10.2 Drag Lab Revision |  |  |  |  | 0
|  |  |  | - | Make retrieval rod not threaded so that it doesn't pull up so much glycerin
|  |  |  | - | Make changes as per the notes taken by D.H.
11 Phys 365 Labs - Coordinator M.I-K.
|  |  | 11.1 Template |  |  |  |  | 0
12 Phys 369 Labs - Coordinator M.I-K.
|  |  | 12.1 Template |  |  |  |  | 0
13 Phys 375 Labs - Instructor W.T.
|  |  | 13.1 Michelson Interferometer |  |  |  |  | 3
|  |  |  | - | Divergent beam component removed
|  |  |  | - | Evolution of wave through interferometer added
|  |  |  | - | Companion guide updated
|  |  |  | - | Approved by instructor, technicians, TLDC, and AHU
|  |  | 13.2 Minor Corrections |  |  |  |  | 0
|  |  |  | - | Minor corrections made to the remainder of the labs in response to feedback
|  |  |  | - | Approved by instructor, technicians, TLDC, and AHU
|  |  | 13.3 Photodetectors for Coherence Length of Light Lab |  |  |  |  | 0
|  |  | 13.4 Companion Guides |  |  |  |  | 0
14 Phys 397 Labs - Instructor A.H.
|  |  | 14.1 Minor Corrections |  |  |  |  | 0
|  |  |  | - | Minor corrections made to the remainder of the labs in response to feedback
|  |  |  | - | Approved by instructor, technicians, TLDC, and AHU
15 Phys 497 Labs - Instructor M.W.
|  |  | 15.1 Electronics Labs Improved |  |  |  |  | 2
|  |  |  | - | Labs tested by instructor
Corrections made to write-up in response to comments from instructor
|  |  |  | - | Changes to lab write-up approved by instructor and AHU
16 Phys 597 Labs - Instructor A.L.
|  |  | 16.1 Laser Safety for Quantum Lab |  |  |  |  | 3
|  |  |  | - | Laser safety document written
|  |  |  | - | Barriers for laser constructed
|  |  |  | - | Equipment shelving constructed
|  |  |  | - | Photon detector protection built
|  |  |  | - | Power supplies connectors built
|  |  |  | - | Laser registered with safety office

## Activites
| PJL Major Projects FA2017 | o | ml | p | raw |  | Action Time | Action Cost | Total Time | Total Cost | Completed | Requires
1.1.1a | Build downloading functions | 1 | 3 | 7 | 3.3333 | SS Hrs | 4 |  |  |  |  | 1.1.1c
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
1.1.1b | Build sorting function. Add searching by ID number. Include "No Year" when searching by "most recent". Sort then filter | 1 | 3 | 7 | 3.3333 | SS Hrs | 4 |  |  |  |  | 1.1.1a
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.1.1c | Build landing page. Build place for Safety Document, student documents (future home of "student guides"), lab schedules, templates. | 5 | 10 | 21 | 11 | SS Hrs | 11 |  |  |  |  | Start
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.1.1d | Add funtion for reporting issues | 4 | 5 | 10 | 5.6667 | SS Hrs | 6 |  |  |  |  | 1.1.1h
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.1.1e | Write a document that oulines how the website functions | 14 | 21 | 35 | 22.1667 | SS Hrs | 23 |  |  |  |  | 1.1.1f 1.1.4a 1.1.4b
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.1.1f | Security audit and changes made to website in response to findings |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.1d
|  | 10 | 14 | 35 | 16.8333 | Tech | 17
[5 empty] | 0 | Cost |  | 0
1.1.1g | Hand over administration to PJL | 14 | 21 | 28 | 21 | SS Hrs | 21 |  |  |  |  | 1.1.1e
|  | 14 | 21 | 28 | 21 | Tech | 21
[5 empty] | 0 | Cost |  | 0
1.1.1h | Integrate equipment xml with pjl website. This includes displaying relavent equipment information in drop down menu of individual labs | 5 | 7 | 21 | 9 | SS Hrs | 9 |  |  |  |  | 1.1.1b
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 116 | 0
1.1.2a | Standardize equipment lists in repository xml |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | Start
|  | 28 | 35 | 42 | 35 | Tech Hrs | 35
[5 empty] | 0 | Cost |  | 0
1.1.2b | Assign topics and disciplines to all labs |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2a
|  | 35 | 49 | 70 | 50.1667 | Tech | 51
[5 empty] | 0 | Cost |  | 0
1.1.2c | Compile Support Documents for current labs |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2b
|  | 50 | 70 | 105 | 72.5 | Tech | 73
[5 empty] | 0 | Cost |  | 0
1.1.2d | Compile Support Documents for non-current labs |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2c
|  | 50 | 70 | 105 | 72.5 | Tech | 73
[5 empty] | 0 | Cost |  | 0
1.1.2e | Build list of alternate equipment in equipment xml |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2a
|  | 5 | 7 | 14 | 7.8333 | Tech | 8
[5 empty] | 0 | Cost |  | 0
1.1.2f | Compile all existing data for current labs |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2b
|  | 7 | 10 | 14 | 10.1667 | Tech | 11
[5 empty] | 0 | Cost |  | 0
1.1.2g | Compile all existing date for non-current labs |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2f
|  | 7 | 10 | 14 | 10.1667 | Tech | 11
[5 empty] | 0 | Cost |  | 0
1.1.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 262 | 0
1.1.3a | Add all standard equipment to xml |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.2e
|  | 28 | 35 | 49 | 36.1667 | Tech Hrs | 37
[5 empty] | 0 | Cost |  | 0
1.1.3b | Compile Manuals for Equipment |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.3a
|  | 125 | 150 | 200 | 154.1667 | Tech | 155
[5 empty] | 0 | Cost |  | 0
1.1.3c | Confirm that equipment xml matches repository xml |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.3a
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.1.3d | Write a document that outlines how the equipment database is built |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.4c
|  | 6 | 7 | 14 | 8 | Tech | 8
[5 empty] | 0 | Cost |  | 0
1.1.3e | Inventory equipment including location(s) |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.3g
|  | 10 | 14 | 21 | 14.5 | Tech | 15
[5 empty] | 0 | Cost |  | 0
1.1.3f | Move non-standard equipment to storage room 20 or 25A |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.3c
|  | 10 | 14 | 21 | 14.5 | Tech | 15
[5 empty] | 0 | Cost |  | 0
1.1.3g | Reorganize standard equimpent in lab rooms |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.3f
|  | 10 | 14 | 21 | 14.5 | Tech | 15
[5 empty] | 0 | Cost |  | 0
1.1.3h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 251 | 0
1.1.4a | Build automated method for adding new versions | 5 | 6 | 7 | 6 | SS Hrs | 6 |  |  |  |  | Start
|  | 5 | 6 | 7 | 6 | Tech Hrs | 6
[5 empty] | 0 | Cost |  | 0
1.1.4b | Build automated method for adding new lab | 5 | 6 | 7 | 6 | SS Hrs | 6 |  |  |  |  | Start
|  | 5 | 6 | 7 | 6 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.1.4c | Build tool for updating status of equipment | 5 | 6 | 7 | 6 | SS Hrs | 6 |  |  |  |  | 1.1.3a
|  | 5 | 6 | 7 | 6 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.1.4d | Build automated method for updating webpage on server |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.1g
|  | 2 | 3 | 7 | 3.5 | Tech | 4
[5 empty] | 0 | Cost |  | 0
1.1.4e | Write a mantainance guide for the websits |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.4a 1.1.4b 1.1.3a
|  | 24 | 28 | 35 | 28.5 | Tech | 29
[5 empty] | 0 | Cost |  | 0
1.1.4f | Compile all documentation for website |  |  |  | 0 | SS Hrs | 0 |  |  |  |  | 1.1.1e 1.1.4e 1.1.3d
|  | 5 | 6 | 7 | 6 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.1.4g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.1.4h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 75 | 0
1.2a | Upgrade electrical | 6 | 7 | 14 | 8 | Other Hrs | 8
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
1.2b | Designate and organize space for parts |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.2c | Designate and organize space for broken equipment |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.2d | Designate and organize space for tools |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.2e | Designates and organize space for manuals |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.2f | Designate and organize space for repaired equipment |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 7 | 5.1667 | Tech | 6
[5 empty] | 0 | Cost |  | 0
1.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
1.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 38 | 0
2.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
2.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
2.2a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
2.2b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
2.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
3.1a | Work through all 221 labs looking for technical issues |  |  |  | 0 | SS Hrs | 0
|  | 5 | 7 | 14 | 7.8333 | Tech Hrs | 8
[5 empty] | 0 | Cost |  | 0
3.1b | Collect and compile sample data |  |  |  | 0 | SS Hrs | 0
|  | 7 | 14 | 28 | 15.1667 | Tech | 16
[5 empty] | 0 | Cost |  | 0
3.1c | Write a report on the findings from lab test |  |  |  | 0 | SS Hrs | 0
|  | 2 | 3 | 5 | 3.1667 | Tech | 4
[5 empty] | 0 | Cost |  | 0
3.1d | Correct any technical problems that are identified in testing |  |  |  | 0 | SS Hrs | 0
|  | 7 | 10 | 21 | 11.3333 | Tech | 12
[5 empty] | 0 | Cost |  | 0
3.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
3.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
3.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
3.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 40 | 0
4.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
4.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
4.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
5.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
5.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
5.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
6.1a | Develop an experimental procedure that will allowfor more evenly spaced lines |  |  |  | 0 | SS Hrs | 0
|  | 20 | 24 | 35 | 25.1667 | Tech Hrs | 26
[5 empty] | 0 | Cost |  | 0
6.1b | Modify equipment to accomidate procedural changes |  |  |  | 0 | SS Hrs | 0
|  | 2 | 5 | 21 | 7.1667 | Tech | 8
|  | 0 | 50 | 200 | 66.6667 | Cost |  | 66.6667
6.1c | Test out all equipment to ensure it is functioning correctly |  |  |  | 0 | SS Hrs | 0
|  | 2 | 5 | 21 | 7.1667 | Tech | 8
[5 empty] | 0 | Cost |  | 0
6.1d | Changes to write-up approved by instructor and AHU |  |  |  | 0 | SS Hrs | 0
|  | 1 | 1 | 1 | 1 | Tech | 1
[5 empty] | 0 | Cost |  | 0
6.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 43 | 66.6667
6.2a | Develop a reliable experimental procedure and recommend equipment changes |  |  |  | 0 | SS Hrs | 0
|  | 28 | 35 | 70 | 39.6667 | Tech Hrs | 40
[5 empty] | 0 | Cost |  | 0
6.2b | Procure new equipment |  |  |  | 0 | SS Hrs | 0
|  | 4 | 5 | 14 | 6.3333 | Tech | 7
|  | 150 | 200 | 300 | 208.3333 | Cost |  | 208.3333
6.2c | Changes to write-up approved by instructor and AHU |  |  |  | 0 | SS Hrs | 0
|  | 1 | 1 | 1 | 1 | Tech | 1
[5 empty] | 0 | Cost |  | 0
6.2d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.2e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.2f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 48 | 208.3333
6.3a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
6.3b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.3h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
6.4a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
6.4b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
6.4h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
7.1a | Test how long playdoe can be exposed to air before it is too dry |  |  |  | 0 | SS Hrs | 0
|  | 7 | 10 | 14 | 10.1667 | Tech Hrs | 11
[5 empty] | 0 | Cost |  | 0
7.1b | Develop a procedure for re-hydrating playdoe |  |  |  | 0 | SS Hrs | 0
|  | 5 | 7 | 10 | 7.1667 | Tech | 8
[5 empty] | 0 | Cost |  | 0
7.1c | Write a document outlining operational plan for playdoe lab |  |  |  | 0 | SS Hrs | 0
|  | 3 | 4 | 6 | 4.1667 | Tech | 5
[5 empty] | 0 | Cost |  | 0
7.1d | Procure playdoe |  |  |  | 0 | SS Hrs | 0
|  | 1 | 2 | 3 | 2 | Tech | 2
[5 empty] | 0 | Cost |  | 0
7.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
7.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
7.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
7.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 26 | 0
8.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
8.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
8.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.2a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.2b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.3a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.3b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.3h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.4a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.4b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.4h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.5a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.5b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.5h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.6a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.6b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.6h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
9.7a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
9.7b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
9.7h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
10.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
10.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
10.2a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
10.2b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
10.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
11.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
11.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
11.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
12.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
12.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
12.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
13.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
13.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
13.2a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
13.2b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.2h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
13.3a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
13.3b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.3h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
13.4a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
13.4b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
13.4h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
14.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
14.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
14.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
15.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
15.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
15.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0
16.1a |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech Hrs | 0
[5 empty] | 0 | Cost |  | 0
16.1b |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1c |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1d |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1e |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1f |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1g |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0
16.1h |  |  |  |  | 0 | SS Hrs | 0
[5 empty] | 0 | Tech | 0
[5 empty] | 0 | Cost |  | 0 | 0 | 0

## Gantt - Working Copy
Gantt Chart | %WP | Completed |  | Budgeted | Actual | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22
1.1.1a | 3.448% | 0 | SS Hrs | 4 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.1b | 3.448% | 0 | SS Hrs | 4 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.1c | 9.483% | 0 | SS Hrs | 11 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.1d | 5.172% | 0 | SS Hrs | 6 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.1e | 19.83% | 0 | SS Hrs | 23 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.1f | 14.66% | 0 | SS Hrs | 0 | 0
|  |  | Sci IT | 17 | 0
|  |  | Cost | 0 | 0
1.1.1g | 36.21% | 0 | SS Hrs | 21 | 0
|  |  | Tech Hrs | 21 | 0
|  |  | Cost | 0 | 0
1.1.1h | 7.759% | 0 | SS Hrs | 9 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.2a | 13.36% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 35 | 0
|  |  | Cost | 0 | 0
1.1.2b | 19.47% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 51 | 0
|  |  | Cost | 0 | 0
1.1.2c | 27.86% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 73 | 0
|  |  | Cost | 0 | 0
1.1.2d | 27.86% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 73 | 0
|  |  | Cost | 0 | 0
1.1.2e | 3.053% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 0 | 0
1.1.2f | 4.198% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 11 | 0
|  |  | Cost | 0 | 0
1.1.2g | 4.198% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 11 | 0
|  |  | Cost | 0 | 0
1.1.2h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.3a | 14.74% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 37 | 0
|  |  | Cost | 0 | 0
1.1.3b | 61.75% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 155 | 0
|  |  | Cost | 0 | 0
1.1.3c | 2.39% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.1.3d | 3.187% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 0 | 0
1.1.3e | 5.976% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 15 | 0
|  |  | Cost | 0 | 0
1.1.3f | 5.976% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 15 | 0
|  |  | Cost | 0 | 0
1.1.3g | 5.976% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 15 | 0
|  |  | Cost | 0 | 0
1.1.3h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.4a | 16% | 0 | SS Hrs | 6 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.1.4b | 16% | 0 | SS Hrs | 6 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.1.4c | 16% | 0 | SS Hrs | 6 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.1.4d | 5.333% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 4 | 0
|  |  | Cost | 0 | 0
1.1.4e | 38.67% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 29 | 0
|  |  | Cost | 0 | 0
1.1.4f | 8% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.1.4g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.1.4h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.2a | 21.05% | 0 | Other Hrs | 8 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.2b | 15.79% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.2c | 15.79% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.2d | 15.79% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.2e | 15.79% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.2f | 15.79% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 6 | 0
|  |  | Cost | 0 | 0
1.2g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
1.2h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
2.2h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
3.1a | 20% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 0 | 0
3.1b | 40% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 16 | 0
|  |  | Cost | 0 | 0
3.1c | 10% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 4 | 0
|  |  | Cost | 0 | 0
3.1d | 30% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 12 | 0
|  |  | Cost | 0 | 0
3.1e | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
3.1f | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
3.1g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
3.1h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
4.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
5.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.1a | 60.47% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 26 | 0
|  |  | Cost | 0 | 0
6.1b | 18.6% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 66.6667 | 0
6.1c | 18.6% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 0 | 0
6.1d | 2.326% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 1 | 0
|  |  | Cost | 0 | 0
6.1e | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.1f | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.1g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.1h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.2a | 83.33% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 40 | 0
|  |  | Cost | 0 | 0
6.2b | 14.58% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 7 | 0
|  |  | Cost | 208.3333 | 0
6.2c | 2.083% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 1 | 0
|  |  | Cost | 0 | 0
6.2d | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.2e | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.2f | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.2g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.2h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.3h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
6.4h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
7.1a | 42.31% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 11 | 0
|  |  | Cost | 0 | 0
7.1b | 30.77% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 8 | 0
|  |  | Cost | 0 | 0
7.1c | 19.23% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 5 | 0
|  |  | Cost | 0 | 0
7.1d | 7.692% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 2 | 0
|  |  | Cost | 0 | 0
7.1e | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
7.1f | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
7.1g | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
7.1h | 0% | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
8.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.2h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.3h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.4h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.5h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.6h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
9.7h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
10.2h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
11.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
12.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.2h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.3h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
13.4h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
14.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
15.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1a | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1b | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1c | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1d | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1e | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1f | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1g | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0
16.1h | #DIV/0! | 0 | SS Hrs | 0 | 0
|  |  | Tech Hrs | 0 | 0
|  |  | Cost | 0 | 0

## PDM
Precidence Diagraming Method - Major Projects 2017
| 11 | 11 |  | 4 | 15 |  | 4 | 19 |  | 9 | 28 |  | 6 | 34 |  | 17 | 51 |  | 23 | 74 |  | 42 | 74 |  | 6 | 80
1.1.1c |  |  | 1.1.1a |  |  | 1.1.1b |  |  | 1.1.1h |  |  | 1.1.1d |  |  | 1.1.1f |  |  | 1.1.1e |  |  | 1.1.1g |  |  | 1.1.4d
| WK |  |  | WK |  |  | WK |  |  | WK |  |  | WK |  |  | PG | SCI |  | WK |  | WK | PG |  |  | PG
[12 empty] | 0 | 12 | 12
1.1.4a
[12 empty] | WK | PG
[12 empty] | 0 | 12 | 12
1.1.4b
[12 empty] | WK | PG
[19 empty] | 29 | 109 |  |  |  |  | 6 | 115
[18 empty] | 1.1.4e | [5 empty] | 1.1.4f
[19 empty] | PG | [5 empty] | PG
[19 empty] | 12 | 92 |  | 8 | 100
[18 empty] | 1.1.4c |  |  | 1.1.3d
|  |  |  | 8 | 43 | [10 empty] | 37 | 80 | WK | PG |  |  | PG
|  |  | 1.1.2e | [11 empty] | 1.1.3a
0 | 35 | 35 |  | PG | [11 empty] | PG |  |  | 5 | 85 |  | 15 | 100 |  | 15 | 115 |  | 15 | 130
1.1.2a | [17 empty] | 1.1.3c |  |  | 1.1.3f |  |  | 1.1.3g |  |  | 1.1.3e
| PG | [17 empty] | PG |  |  | PG |  |  | PG |  |  | PG
[19 empty] | 154 | 234
1.1.3b
[7 empty] | 73 | 159 |  | 73 | 232 | [7 empty] | SS
[6 empty] | 1.1.2c |  |  | 1.1.2d
|  |  |  | 51 | 86 |  | PG |  |  | PG
1.1.2b
|  |  |  | PG |  |  | 11 | 97 |  | 11 | 108
[6 empty] | 1.1.2f |  |  | 1.1.2g
[7 empty] | PG |  |  | PG